## Stakeholder Register
Stakeholder Name | Stakeholder Role | Stakeholder Contact Information | Stakeholder Interest | Stakeholder Influence | Stakeholder Needs and Concerns | Stakeholder Engagement Plan | Stakeholder Risk Assessment
John Smith | Project Sponsor | john.smith@email.com, (123) 456-7890 | High | High | Wants the project to be completed on time and within budget | Will meet with John weekly to discuss progress and address any concerns | Low risk of John delaying the project or exceeding the budget
Jane Doe | Customer | jane.doe@email.com, (987) 654-3210 | High | Low | Wants the project to meet her needs and expectations | Will send Jane weekly updates on the project and solicit her feedback | Low risk of Jane being dissatisfied with the project
Bill Jones | Supplier | bill.jones@email.com, (555) 444-3333 | Medium | Medium | Wants to be paid on time and wants to ensure that the project is completed to their specifications | Will meet with Bill weekly to discuss progress and ensure that he is meeting the project's needs | Medium risk of Bill delaying the project or delivering goods or services that do not meet the project's specifications
Mary Brown | Regulatory Body | mary.brown@email.com, (777) 888-9999 | Low | High | Wants to ensure that the project complies with all applicable regulations | Will send Mary monthly updates on the project and keep her informed of any changes to the project plan | Low risk of Mary delaying the project or preventing it from being completed
Susie Jones | Risk Manager | susie.jones@email.com, (777) 888-9999 | High | High | Wants to ensure that the project assess and mitigatges risks appropriately | Will send Mary the weekly project risk reports on the project and keep her informed of any new risks. | Low risk of Mary delaying the project or preventing it from being completed